## Overall Projects
Sector | S.No. | Project | Land requirement | 2018 |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
|  |  |  | April-June | July-Sept | Oct- Dec | Jan- March | April-June | July-Sept | Oct- Dec | Jan- March | April-June | July-Sept | Oct- Dec | Jan- March | April-June | July-Sept | Oct- Dec | Jan- March | April-June | July-Sept | Oct- Dec | Jan- March | April-June | July-Sept | Oct- Dec
City Profile | 1 | Geo-tagging of all properties in X Nagar Palika Parishad and categorisation of them (residnetial, institutional and commercial) | None
Water Supply | 2 | Water Audit of existing water supply infrastructure | none
| 3 | Energy Audit of existing water supply infrastructure | none
| 4 | Technical Intervention to stop water losses at point of extraction (water is byepassed to flow in drains) due to high pressure. | none
| 5 | Creation of additional infrastructure (Overhead tanks) for the augmented water supply in Bijnor Nagar Palika Parishad | Government land available
| 5 a) | 1. Feasibility study by Dec 2019
| 5 b) | 2. Preparation and approval of DPR
| 5 c) | 3. Implementation of DPR to be commenced from April 2021
Access to toilets | 6 | Retrofitting of 5 Public Toilets (PTs) | none
| 7 | Retrofitting of 9 Urinals | none
| 8 | Retrofitting of 3 Community Toilets (CTs) | none
| 9 | Construction of new 11 PTs | 40 sq m per PT (government land available for 7 PTs and private land to be procured for 4 PTs)
| 10 | Construction of 2 'Saniplex' | 100 sq m per site (government land available)
Wastewater and FSSM | 11 | All properties to be connected to sewer at a subsidised charges | none
| 12 | Faecal sludge treatment plant | 1000 sq. m
| 12 a) | Preliminary site assessment
| 12 b) | FSTP operational
| 13 | Pilot scale decentralised wastewater treatment system (DWWTs) at existing community toilet near Ravidas Mandir | 100 sq. m (available)
| 13 a) | DPR preparation and approval
| 13 b) | DWWTs Operational
| 14 | Pilot scale decentralised wastewater treatment system (DWWTs) at Vikas Bhavan | 100 sq. m (available)
| 14 a | DPR preparation and approval
| 14 b | DWWTs Operational
| 15 | Pilot scale decentralised wastewater treatment system (DWWTs) at District Collector Office | 70 sq. m (available)
| 15 a | DPR preparation and approval
| 15 b | DWWTs Operational
Solid Waste Management | 16 | Segregation at source for households in Bijnor Area | None
| 17 | Establishing transfer stations | Approx 5000 sqm each for compaction and segregation
| 18 | Model Processing and treatment Unit for ward 3 at open land near Meerut Chungi Community Toilet | 400 sq m for composting in city
| 19 | Treatment of Mandi Waste through Vermi composting | 2000 sq m
| 20 | IEC regarding good solid waste management practices through schools and capacity building of ULB staff | None
| 21 | Recognising Informal sector | None
Storm Water Management | 22 | Geo mapping of all major(17 no.s) and minor drains | none
| 23 | Mapping of all water logged areas (six) and ponds (four) | none
| 24 | Channeling storm water with SUDS to open land near Ravidas Mandir and/or Indira Park | Government(Forest) land, required land to be calculated based on the flow in drains
| 25 | Restoration of water body like Ganga Devi Mandir pond | Government land
| 26 | Raiwater Harvesting structures for storage and reuse at Vardhaman college and for recharge at New Tehsil office | Private land, there is enough land available in college and Tehsil office

## City Level
A | City Profile | Details | Time frame | Land requirement
A.1

## Water Supply
A | Water Supply | Details | Time Line | Land requirement
A.1 | Water Audit of existing water supply infrastructure | 1. 24 Tube wells | By Dec 2019 | none
2. 8 Overhead tanks (Total cap: 8650 KL)
3. Rising Main: 31.03 km
4. Distribution Line: 115.748 km
A.2 | Energy Audit of existing water supply infrastructure | 1. 24 Tube wells | By Dec 2019 | none
2. 24 Pumps (from 12.5 hp to 41 hp)
3. Power transmission line: 11 KV - HT Line: 4 km
A.3 | Technical Intervention to stop water losses at point of extraction (water is byepassed to flow in drains) due to high pressure. | All 24 tube wells discharge part of extracted water into drains to release extra pressure; the pipelines can not sustain high pressure. There is one technology called pressure release valve (PRV), installation of PRV at each tube well (25 nos.) can release the extra pressure and will save wastage of water. | By Dec 2020 | none
A.4 | Creation of additional infrastructure (Overhead tanks) for the augmented water supply in Bijnor Nagar Palika Parishad | Currently, there are only 8 OHTs connected to 12 Tube wells. Remaining 12 Tube wells supply water directly to the Households. Hence we propose to create extra OHTs (8 nos, total capacity: 8650 KL) and replacing of the old pipelines directly supplying water. This project will have following three phases; | By Dec 2023 | Government land available
1. Feasibility study by Dec 2019
2. Preparation of DPR (inputs to be taken from the findings of water audit) by Dec 2020
3. Implementation of DPR to be commenced from April 2021

## Access to Sanitary Toilet
| Access to sanitary toilets | Details | Time Line | Land requirement
A.1 | Retrofitting of 5 Public Toilets (PTs) | Signage on streets | By Dec. 2018 | none
Ramp
Mirror
Availability of handwashing agent and hand drying facility
Repair of water closet, and flush tanks
Repair of fixtures (water efficient)
Lighting and exhaust fans (energy efficient)
Toilet facility for differently abled
Provision for dust bins
Provision for sanitary pad dispensing machine
Provision for scientific disposal of used sanitary pads
Appointment of dedicated female cleaning staff
Availability of First aid box
Connecting with sewer line
Bathroom fresheners
Complaint and suggestion box
Spitoon
Wall pegs
A.2 | Retrofitting of 9 Urinals | Shed to cover the urinal | By Dec. 2018 | none
Front wall (made of fly ash or other reused material) for privacy from passerbys
Repair of urinals
Connection with sewer lines
Signage
Handwashing facility
Errecting urinals for females (1 at each location)
Provision for sanitary pad dispensing machine
Provision for scientific disposal of used sanitary pads
Complaint and suggestion box
A.3 | Retrofitting of 3 Community Toilets (CTs) | Ramp | By Dec. 2018 | none
Mirror
Availability of handwashing agent and hand drying facility
Repair of water closet, and flush tanks (reusable material)
Repair of fixtures (water efficient)
Lighting and exhaust fans (energy efficient)
Toilet facility for differently abled and below 6 yr children
Provision for dust bins
Provision for sanitary pad dispensing machine
Provision for scientific disposal of used sanitary pads
Appointment of dedicated female cleaning staff
Availability of First aid box
Connecting with sewer line
Bathroom fresheners
Complaint and suggestion box
Spitoon
Wall pegs
covered bathing and cloth washing facility
Installation of RWH structure (roof top with sump)
In block male and female signage
B | Construction of new 11 PTs | 1. Males: 2 Indian seats, 1 Western, 3 urinals Females: 2 Indian seats, 1 Western, 3 urinals 2. Washbasins: 2 for adults in each block; 1 for children <7 years 3. Cubicle for differently-abled as per building bye-laws: 1 in each block 4. Seats for children <7 years : 1 in each block 5. Remaining features as mentioned in A.1 | By June 2019 | 40 sq m per PT (government land available for 7 PTs and private land to be procured for 4 PTs)
C | Construction of 2 'Saniplex' | Drinking water kiosk | By Dec. 2019 | 100 sq m per site (government land available)
1. Males: 10 Indian seats, 2 Western, 3 urinals Females: 10 Indian seats, 2 Western, 3 urinals 2. Washbasins: 4 for adults in each block; 2 for children <7 years 3. 2 Cubicle for differently-abled as per building bye-laws: 1 in each block 4. Seats for children <7 years : 2 in each block
Solid Waste recyling machine
Provision for seggregated waste
Bathing facility
Washing facility
First aid box
All fixtures to be water efficient
Light fixtures to be energy efficient
Hand washing and drying facilities
Connection to sewer lines
CCTV installation for monitoring
Dedicated male and female staff
Air purifiers
Proper ventilation provisions
Formal redressal mechanism
Power back-up
Wall pegs/hangers
Provisions for hot and cold water
Spitoons outside toilet cubicles
RWH system (given as a separate detailed project)
Sanitary pad dispensing machines
Scientific disposal of toiletries and sanitary products
User charge
Ramps
Cubicles for differently-abled
Provisions for seats and washbasins fitted for small children
Separate doors for entrance of different genders
DWWTs (given as a separate detailed project)
Installation of solar panels
Fire extinguisher
Aesthetic landscaping of the complex

## Storm Water Management
A | Stormwater management and receiving water bodies | Details | Time Line | Land requirement
A.1 | Geo mapping of all major(17 no.s) and minor drains | Flow, direction, carrying capacity, slope, crossection, outfalls, length of kuccha and pukka drains, extent of covered drains | By March 2019 | none
Approximate length 80 Kms
A.2 | Mapping of all water logged areas (six) and ponds (four) | Capacity of ponds and water logged areas | By March 2019 | none
Catchment area and source of water
Quality of water of each water body to be tested according to CPCB standards- 42 samples each in one year (3 times 14 samples) for ponds and 14 samples each for water logged areas
A.3 | Channeling storm water with SUDS to open land near Ravidas Mandir and/or Indira Park | Drain near mandir and Indira park to be channelised, around 100 metres on either side | By March 2020 | Government(Forest) land, required land to be calculated based on the flow in drains
Part of the open land can be used as soft landscape to moderate and attenuate the flow
A.4 | Restoration of water body like Ganga Devi Mandir pond | Treatment of polluted stormwater coming via tivdi drain, through wetland plants before it outfalls into pond | By December 2019 | Government land
Ensure vegetative shoreline buffer around the pond
A.5 | Raiwater Harvesting structures for storage and reuse at Vardhaman college and for recharge at New Tehsil office | Rooftop RWH with minimum treatment like screening/desilting etc. on both sites | By December 2019 | Private land, there is enough land available in college
Two storage sump wells (of capacity 480 cum and 320 cum) with a pump to reuse the water for horticulture at Vardhaman college
|  | Recharge well with bore upto first permeable soil layer, for recharge of rooftop rainwater at Tehsil office |  | Government land

## Wastewater & Faecal Sludge
A | Wastewater and faecal sludge | Details | Time Line | Land requirement
A.1 | All properties to be connected to sewer at a subsidised charges | 16902 properties | By Dec. 2018 | none
30 Public and community toilets
The one time connection charges to be waived off or subsidised
Sewer line is ready
A.2 | Faecal sludge treatment plant | Capacity: 10 KLD | Preliminary site assessment by Sept 2018 | 1000 sq. m
|  | Technology: Unplanted Sludge Drying bed+ Planted gravel filter+Maturation pond | Land procurement and Soil tetsing by Dec 2018
|  | Procurement of two vacutug (truck): one of 1.5 KL and second of 4 KL and land | Preparation and approval of DPR by April 2019
|  | Registration and licensing of existing desludgers | Commencement of construction by July 2019
|  | IEC campaign | Procurement of vacutugs and training of operators by Dec 2019
|  | Training of vacutug operators | Operational from Jan 2020
A.3 | Pilot scale decentralised wastewater treatment system (DWWTs) at existing community toilet near Ravidas Mandir | Capacity: 10 KLD | DPR preparation and approval by Nov 2018 | 100 sq. m (available)
|  | Technology: Anaerobic baffle reactor + Planted gravel filter + Maturation pond | Commencement of construction by Jan 2019
|  | The existing septic tank to be modified into a biogas digester | Operation from April 2019
Use of generated biogas for the lighting purpose in community toilet (23 gas bulbs)
A.4 | Pilot scale decentralised wastewater treatment system (DWWTs) at Vikas Bhavan | Capacity: 20 KLD | DPR preparation and approval by Nov 2018 | 100 sq. m (available)
|  | Technology: Soil Biotechnology (patented technology by IIT Bombay) | Commencement of construction by Feb 2019
|  | GI pipe (4 inch, 200m)to take treated water for reuse/recycling | Operation from June 2019
A.5 | Pilot scale decentralised wastewater treatment system (DWWTs) at District Collector Office | Capacity: 10 KLD | DPR preparation and approval by Nov 2018 | 70 sq. m (available)
|  | Technology: phytorid (NEERI patented technology) | Commencement of construction by Jan 2019
|  | GI pipe (4 inch, 200m) to take treated water for reuse/recycling | Operation from April 2019

## Solid waste
A | Solid waste | Details | Time Line | Land requirement
A.1 | Segregation at source for households in Bijnor Area | DPR Preparation - 1_requirement of two bins (green and blue) per household (No of HH - 16,600) of capacity 10-14litres | 2019-09-01 | None
2_Purchase and color coding of community bins (28-36 Nos. of bins of capacity 60litres - residential areas; 6-10 Nos. of bins of capacity 110litres - Market/ Bulk waste generator)
3_Retrofitting of existing 19 vehicles (partitioning for collection of segregated dry and wet waste)
4_Purchase of equipments (Pans; spades, PPE - gloves, mask, uniforms, boots etc for 100 new safai karamcharis and 17 drivers) and vehicles that support collection and handling of segregated waste (17 LCV with partition for collection of segregated waste); Push carts for waste collection from accessible households (40 Nos.)
5_Recruitment of new staff and their training (100 safai karamchari; 17 drivers for LCV)
6_Capacity building of existing staff(285 Safai karamchari and drivers); BCC and IEC campaign for all stakeholders
A.2 | Establishing transfer stations | Procuring compactors (4 Nos. of capacity 25 cu m) | 2019-09-01 | Approx 5000 sqm each for compaction and segregation
Recruiting and training of staff
Possible sites: open land near Ravidas mandir, near Meerut Chungi CT, numaish ground
A.3 | Model Processing and treatment Unit for ward 3 at open land near Meerut Chungi Community Toilet | Hiring of consultants for DPR Preparation - Waste characterization and then accordingly identification of processing technology | 2020 | 400 sq m for composting in city
This pocket of land can be used for processing of waste for Ward 3 and then the capacity of the plant can be expanded to take care of a cluster of wards
A.4 | Treatment of Mandi Waste through Vermi composting | Identification of land for composting 5 tonnes of mandi waste along with Faecal Sludge | 2018 | 2000 sq m
A.5 | IEC regarding good solid waste management practices through schools and capacity building of ULB staff | Students and teachers drives for swachhta | 2018 | None
Competition between scools for model solid waste management
Advertisements, pamphlets, posters etc.
Exposure visits, practical training
A.6 | Recognnising Informal sector | 1_Registration, licensing and training of rag pickers and scrap dealers | 2019-09-01 | None